## Logic Model
Project Title: Safe Start, Brighter Future
Overall Goal: To reduce U5MR among refugee and impoverished Lebanese children.
Input | Activities | Output | Outcome | Impact
Funding, Human Resources, Materials, Infrastructure, Partnerships | 1. Healthcare Services: Mobile clinics, PHC strengthening, staff incentives, vaccination campaigns, medicine provision, referrals. | 1. Healthcare Access: # mobile clinics, # PHCs supported, # staff trained, # vaccines administered, # consultations. | 1. Improved Health Utilization: % children fully vaccinated, % births with SBA, % sick children seeking care, % PLW attending ANC/PNC. | % reduction in U5MR among target populations. Improved child survival and well-being.
| 2. Health: ANC/PNC, SBA promotion, Community Healthworker (CHW) training. | 2. Health: # ANC/PNC visits, # SBA births, # CHW home visits.
| 3. Nutrition: IYCF counseling, GMP, OTP/TSFP, micronutrient distribution. | 3. Nutrition: # IYCF sessions, # children screened/enrolled, # RUTF/supplements distributed. | 2. Improved Nutrition: % children exclusively breastfed, % reduction in Severe Acute Malnutrition/Moderate Acute Malnutrition, % children with adequate dietary diversity.
| 4. WASH: Hygiene campaigns, kit distribution, infrastructure support. | 4. WASH: # campaigns, # kits, # facilities supported. | 3. Reduced Morbidity: % reduction in diarrheal disease, Acute Respiratory Infections, measles cases.
| 5. Awareness: CHW deployment, health education, community groups. | 5. Awareness: # CHWs, # sessions, # materials distributed.

## Abbreviations
Abbreviation | Full Term | Definition / Usage Context
ANC | Antenatal Care | Health services provided to pregnant women before childbirth; monitored to reduce maternal and neonatal risks.
CHW | Community Health Worker | Local health agents trained to deliver services and education at the community level.
DQA | Data Quality Assessment | Routine or periodic review to verify the accuracy, completeness, and consistency of collected data.
DTP3 | Diphtheria-Tetanus-Pertussis (3rd dose) | A standard childhood vaccine; used as a coverage proxy for full immunization.
EmONC | Emergency Obstetric and Newborn Care | Critical services provided to manage complications during pregnancy, childbirth, and the neonatal period.
FGD | Focus Group Discussion | A qualitative method used to collect perceptions and feedback from beneficiaries or stakeholders.
HMIS | Health Management Information System | National or local data system used to record and monitor health service delivery indicators.
IYCF | Infant and Young Child Feeding | Guidelines and practices that promote optimal nutrition from birth to 2 years of age.
IMCI | Integrated Management of Childhood Illness | A WHO-recommended approach to reduce death and illness in children under 5.
IMR | Infant Mortality Rate | Deaths among children <1 year per 1,000 live births; monitored to assess health system performance.
IPTT | Indicator Performance Tracking Table | A central monitoring tool used to track all project indicators over time against targets.
KAP | Knowledge, Attitudes, and Practices | Surveys used to assess behavioral determinants among target populations.
M&E | Monitoring and Evaluation | A systematic process to track implementation and assess project results.
MAM | Moderate Acute Malnutrition | A nutritional condition in children characterized by moderate wasting; tracked through nutrition screening.
MoPH | Ministry of Public Health | National authority responsible for public health governance in Lebanon.
MUAC | Mid-Upper Arm Circumference | A common anthropometric measurement to identify acute malnutrition in children.
NMR | Neonatal Mortality Rate | Number of deaths among newborns (0–28 days) per 1,000 live births.
ORS | Oral Rehydration Salts | A low-cost treatment for dehydration due to diarrhea; critical for child survival.
OTP | Outpatient Therapeutic Program | A program offering treatment for children with SAM without medical complications.
PNC | Postnatal Care | Services provided to women and newborns in the first 6 weeks after birth.
SAM | Severe Acute Malnutrition | A life-threatening form of malnutrition in children, requiring immediate intervention.
SOP | Standard Operating Procedure | A formal protocol describing how tasks should be executed for consistency and quality.
TSFP | Targeted Supplementary Feeding Program | A program providing nutrition support for children with MAM or at risk of SAM.
U5MR | Under-5 Mortality Rate | Number of deaths of children under 5 per 1,000 live births; a key impact indicator.
WASH | Water, Sanitation, and Hygiene | A sector focused on ensuring safe water, adequate sanitation, and hygiene practices.

## Household Vulnerability Scoring
Domain | Indicator Example | Scoring Range | Data Source | Notes
Socioeconomic | Monthly income or expenditure below poverty line | 0–2 | Household Economic Survey | 2 = severely poor; 1 = near poor; 0 = above poverty threshold
Food Security | Food shortage or reliance on negative coping strategies | 0–2 | rCSI / FCS Module | 2 = severe food insecurity; scored using WFP/FAO methodology
Child Health | U5 child had diarrhea, pneumonia, or SAM in past 2 months | 0–2 | Caregiver interview / Clinic card | Verifiable via survey or health records
Nutrition | Child under 5 with MAM, SAM, or underweight | 0–2 | MUAC measurement / Weight-for-age | Standard nutrition screening protocol
Access to Services | >30 min from PHC or lacks ID/residency documents | 0–2 | GPS / Household survey | 1 = one barrier; 2 = both distance and documentation barriers
WASH Access | No access to improved water and/or sanitation | 0–2 | WASH Household Survey | Uses JMP definitions of improved/unimproved
Household Status | Female-headed, elderly, disabled, or refugee/displaced household | 0–2 | Registration form / Observation | 2 = multiple vulnerability markers; 1 = one; 0 = none
Total Score: 0 - 14
Vulnerability
10 - 14: High
6 - 9: Moderate
0 - 5: Low

## Example of a HHVSS
HH ID# | Socioeconomic | Food Security | Child Health | Nutrition | Access to Services | WASH Access | Household Status | Total Score | Vulnerability Level
HH0001 | 2 | 2 | 1 | 1 | 0 | 1 | 2 | 9 | Moderate
HH0002 | 0 | 0 | 1 | 0 | 1 | 0 | 2 | 4 | Low
HH0003 | 2 | 1 | 1 | 1 | 1 | 2 | 2 | 10 | High

## Indicators Matrix
# | Indicator Description | Baseline | Target | Data Source | Frequency | Disaggregation | Means of Verification | Responsible Party
Indicators at Output Level
1 | # of mobile health clinics established/supported | 0 | 6 | Project records | Quarterly | Location | Field reports | Project Officer
2 | # of PHCs receiving support (medicines, equipment, staff) | 0 | 10 | PHCs/ Partner reports | Quarterly | Type of support, location | Distribution logs | Logistics, MEAL
3 | # of HCWs trained in IMCI, EmONC, nutrition | 0 | 30 | Training attendance | Monthly | Type of training, gender, location | Training logs | Training Lead
4 | # of vaccine doses administered | TBD | TBD | HMIS | Monthly | Vaccine type, gender, age | HMIS export | MoPH, MEAL
5 | # of ANC/PNC visits provided | TBD | TBD | Clinic records | Monthly | Age, trimester | HMIS | MoPH, MEAL
6 | # of IYCF counseling sessions conducted | TBD | TBD | Project records | Monthly | Gender, caregiver type | Session logs | Nutrition Officer
7 | # of children screened for malnutrition | TBD | TBD | OTP/TSFP records | Monthly | Age, gender | Screening forms | Nutrition Team
8 | # of children admitted to OTP/TSFP | TBD | TBD | Clinic registers | Monthly | Program type, age | Admission records | Nutrition Officer
9 | # of hygiene kits distributed | 0 | TBD | Distribution lists | Monthly | Household type | Distribution logs | WASH Team
10 | # of CHWs trained and deployed | 0 | 30 | Training records | Quarterly | Gender, location | Deployment log | CHW Coordinator
11 | # of community health awareness sessions conducted | 0 | TBD | Activity reports | Monthly | Topic, gender | Session records | Health Promotion Team
Outcome Level
12 | % of children 12–23m fully vaccinated (Vaccines against DTP3, Measles, Polio, Rotavirus) | TBD | TBD | Survey, HMIS | Biannual | Gender, nationality | Survey forms | MEAL
13 | % of births attended by skilled personnel | TBD | TBD | HMIS | Monthly | Mother's age, facility (PHC, hospital, etc.) | Delivery records | MoPH
14 | % of mothers attending ≥4 ANC visits | TBD | TBD | Clinic records | Quarterly | Age | HMIS | MoPH
15 | % of newborns receiving postnatal check-up in 2 days | TBD | TBD | Facility records | Monthly | Gender, age | Visit records | MoPH, MEAL
16 | % of children with diarrhea receiving ORS and zinc | TBD | TBD | Survey, HMIS | Quarterly | Gender, age | FGD, registers | MEAL
17 | % of suspected pneumonia cases seeking care | TBD | TBD | Household survey | Annually | Gender, district | Survey records | MEAL
18 | % of infants 0–5m exclusively breastfed | TBD | TBD | Nutrition survey | Quarterly | Gender | Nutrition forms | Nutrition Officer
19 | % of children 6–23m receiving min. acceptable diet | TBD | TBD | IYCF survey | Biannual | Gender | Diet recall logs | MEAL/Nutrition
20 | Prevalence of SAM and MAM among U5 children | TBD | TBD | Screening surveys | Quarterly | Age, gender | MUAC forms | Nutrition Team
21 | % of HHs with access to improved water source | TBD | TBD | WASH survey | Biannual | Rural/urban | Survey reports | WASH Officer
22 | % of HHs with improved sanitation | TBD | TBD | WASH survey | Biannual | Type, gender of head | Facility verification | WASH Team
23 | % of mothers showing handwashing practices | TBD | TBD | Observations, survey | Quarterly | Gender, location | FGD, KAP survey | MEAL/WASH
24 | % of caregivers IDing ≥3 danger signs | TBD | TBD | KAP survey | Quarterly | Gender, education | Survey forms | MEAL
Impact Level
25 | Under-5 Mortality Rate (per 1,000 live births) | 18.3 | 15 | WHO, UNICEF, World Bank, MoPH | Annually | Gender, vulnerability status, nationality | Survey, UN, WHO and World Bank reports | MEAL, MoPH
26 | Neonatal Mortality Rate (per 1,000 live births) | 11.2 | 8 | MoPH, facility records | Annually | Gender, vulnerability status, nationality | Survey, UN, WHO and World Bank reports | MEAL
27 | Infant Mortality Rate (per 1,000 live births) | 15.6 | 12 | Vital registration statistics | Annually | Gender, vulnerability status, nationality | Mortality survey | MoPH
28 | Prevalence of stunting among U5 children | 7% (25% among Syrian refugees, 10.5% among Palestinians | 5% | Srvey, nutrition assessment | Annually | Gender, vulnerability status, nationality | Anthropometric data | Nutrition Lead

## Strategic Alignment Matrix
The M&E system for the U5MR project is directly informed by the root causes and programmatic pillars outlined in the Problem-Solving Framework for Under-5 Mortality in Lebanon. The framework identifies proximal and distal determinants contributing to excess U5MR, including limited access to primary healthcare, poor maternal knowledge, malnutrition, inadequate WASH conditions, and systemic challenges such as fragility and underfunded public services.
To ensure tight alignment, the M&E system tracks indicators across three levels (Output, Outcome, Impact) that correspond directly to the framework’s five strategic pillars:
Problem-Solving Pillar | M&E Focus Area(s) | Sample Indicators
1. Strengthening Primary Health Care Systems | PHC support, service coverage, stock availability | # of PHCs supported % of children with pneumonia receiving care ORS stock-out
2. Enhancing Maternal and Newborn Health Outcomes | ANC/PNC coverage, skilled birth attendance, postnatal care | % of births attended by skilled personnel % of mothers attending ≥4 ANC visits % of newborns receiving PNC within 2 days
3. Enhancing Maternal and Child Nutrition | IYCF, breastfeeding, SAM/MAM screening | # of IYCF sessions % exclusively breastfed % receiving minimum acceptable diet
4. Improving WASH Access and Practices | Household WASH access and behavior | % HHs with improved water/sanitation % demonstrating critical handwashing
5. Expanding Community Health & Behavior Change | CHW deployment, awareness, caregiver practices | # CHWs trained % of caregivers knowing ≥3 danger signs # of awareness sessions

## Data Quality Checklist
# | Data Quality Dimension | Checklist Item | Responsible Party | Frequency | Status | Notes
1 | Accuracy | Field staff trained on indicator definitions and data collection tools | MEAL Manager | Quarterly
2 | Accuracy | Validation rules active in digital forms (e.g., Kobo, Excel) | MEAL/IT Officer | One-time/setup
3 | Accuracy | Spot checks conducted to verify reported data | MEAL Officer | Monthly |  | Target: 3 facilities per month
4 | Accuracy | Triangulate data from HMIS, surveys, and service records | MEAL Manager | Quarterly |  | Needed for IPTT validation
5 | Timeliness | Data reporting calendar maintained and shared | MEAL Manager | Monthly update |  | Shared via Google Calendar
6 | Timeliness | Alerts/reminders sent to staff before deadlines | MEAL Officer | Monthly |  | SMS automation to be tested
7 | Completeness | All submitted forms reviewed for missing data | MEAL Officer | Monthly
8 | Completeness | Submission dashboard tracking completion status | MEAL Manager | Weekly |  | Use Tableau or Power BI to create dashboard tracking completion
9 | Consistency | Indicator definitions harmonized across all tools | MEAL Manager | Annually
10 | Consistency | Forms version-controlled and archived | MEAL Officer | As needed
11 | Consistency | DQA conducted using source-doc comparison | MEAL Manager | Biannually
12 | Integrity | Role-based access to data systems enforced | IT/Data Manager | Ongoing |  | Admin rights limited
13 | Integrity | Weekly data backups conducted | IT Officer | Weekly |  | Google Drive auto-backup enabled. Also, data will be exported into external hard drives
14 | Integrity | Confidentiality agreements signed by data staff | HR & MEAL | One-time/setup |  | Template needed
15 | Capacity Building | Refresher training on data quality for MEAL and program staff | MEAL Manager | Quarterly
16 | Capacity Building | Field coaching provided on data collection challenges | MEAL Manager | Monthly
17 | Continuous Improvement | DQA results documented and shared during program review meetings | MEAL Manager | Quarterly

## Data Collection Methods
Data Collection | Description | Timeframe | Method
Routine Health Management Information System (HMIS) | Collect data from supported PHCs and health facilities. | Ongoing throughout program implementation - Monthly/quarterly data collection for output and some outcome indicators from HMIS and routine program reports. Regular internal review meetings. | Mixed
Baseline Survey | Comprehensive baseline survey and data collection from existing sources to establish starting points for all KPIs | 0 - 6 months. | Quantitative
Midterm evaluation | Comprehensive review of progress, identification of challenges, and adjustment of strategies. Includes a limited household survey. | At the midterm of the project period | Mixed
Endline evaluation | Comprehensive assessment of impact against the overall objective and all KPIs. Includes a full household survey. | At the end of the project period | Mixed
Rapid Assessments | For specific issues like disease outbreaks or urgent needs | It varies | Mixed
Focus Group Discussions (FGDs) & Key Informant Interviews (KIIs) | Gather qualitative insights on barriers, facilitators, and perceptions. | Quarterly | Qualitative
Observation | For WASH practices, health facility quality. | Yearly | Qualitative